## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | Introduction to project(Form Filling AI) | MUST HAVE | No Dependency | Ashwitha | 3- Completed
Sprint 2 | Sprint 2 | US-001 | Workflow Creation and Project Goal Document | MUST HAVE | Lucid Chart | Adimulam Mourya | 3- Completed
Sprint 3 | Sprint 3 | US-001 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | MUST HAVE | No Dependency | Dhanush | 2- In Progress
Sprint 4 | Sprint 4 | US-001 | Use Case Research and Preparation | SHOULD HAVE | W3School | Punyavathi | 3- Completed
Sprint 5 | Sprint 5 | US-001 | Transaction Simulator & Synthetic Data Generation | MUST HAVE | Documentation, Research | Dhruv | 3- Completed
Sprint 6 | Sprint 6 | US-001 | Rule-Based Fraud Detection Implementation (Amount, Velocity, Geo) | MUST HAVE | Draw.io | Ashwitha | 3- Completed
Sprint 7 | Sprint 7 | US-001 | Transaction Simulator Development | MUST HAVE | Java | Adimulam Mourya | 3- Completed
Sprint 8 | Sprint 8 | US-001 | Requirement Analysis and Fraud Use Case Identification System | SHOULD HAVE | Java | Dhanush | 3- Completed
Sprint 9 | Sprint 9 | US-001 | System Architecture Design for Fraud Detection Engine | MUST HAVE | Java | Adimulam Mourya | 3- Completed
Sprint 10 | Sprint 10 | US-001 | Transaction Simulator Development | MUST HAVE | Java | Dhruv | 3- Completed
Sprint 11 | Sprint 11 | US-001 | Synthetic Transaction Data Generation | MUST HAVE | Java | Adimulam Mourya | 3- Completed
Sprint 12 | Sprint 12 | US-001 | Feature Extraction for Fraud Analysis | SHOULD HAVE | Java | Adimulam Mourya | 3- Completed
Sprint 13 | Sprint 13 | US-001 | Rule-Based Fraud Detection Implementation (Amount, Velocity, Geo) | MUST HAVE | Java | Dhanush | 2- In Progress
Sprint 14 | Sprint 14 | US-001 | Machine Learning Risk Scoring Logic Integration | MUST HAVE | Java(ML logic Integration) | Adimulam Mourya | 3- Completed
Sprint 15 | Sprint 15 | US-001 | Fraud Reason Mapping and Explainability Logic | MUST HAVE | Java | Dhruv | 3- Completed
Sprint 16 | Sprint 16 | US-001 | Alert Generation and Priority Assignment | SHOULD HAVE | Java | Ashwitha | 2- In Progress
Sprint 17 | Sprint 17 | US-001 | Backend API Development for Alerts and Transactions | MUST HAVE | Java(Spring boot) | Adimulam Mourya | 3- Completed
Sprint 18 | Sprint 18 | US-001 | Database Design and Integration | MUST HAVE | MySQL,Java | Dhanush | 2- In Progress
Sprint 19 | Sprint 19 | US-001 | Alert Review Dashboard UI Design | MUST HAVE | HTML,CSS | Punyavathi | 3- Completed
Sprint 20 | Sprint 20 | US-001 | Filters, Search, and ML Score Display in UI | SHOULD HAVE | HTML,CSS | Dhruv | 3- Completed
Sprint 21 | Sprint 21 | US-001 | End-to-End System Integration | MUST HAVE | JAVA,MySQL | Adimulam Mourya | 3- Completed
Sprint 22 | Sprint 22 | US-001 | Testing, Validation, and Deployment | MUST HAVE | JUnit, MySQL, Render | Adimulam Mourya | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 120 | 35 | 18 | 18 | 16 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Project Introduction and Form Filling Module | 2025-11-27 | 2025-11-29 | Ashwitha | Coding | 3 - Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Workflow Creation and Project Goal Documentation | 2025-11-30 | 2025-12-02 | Adimulam Mourya | Design | 3 - Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Documentation Discussion (Agile Template, Defect Tracker, Unit Testing) | 2025-12-03 | 2025-12-04 | Dhanush | Coding | 3 - Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Fraud Use Case Research and Preparation | 2025-12-05 | 2025-12-08 | Punyavathi | Coding | 3 - Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Transaction Simulator and Synthetic Data Generation | 2025-12-09 | 2025-12-13 | Dhruv | Coding | 3 - Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Rule-Based Fraud Detection Implementation (Amount, Velocity, Geo) | 2025-12-14 | 2025-12-18 | Ashwitha | Coding | 3 - Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Transaction Simulator Enhancement | 2025-12-19 | 2025-12-23 | Adimulam Mourya | Coding | 3 - Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Requirement Analysis and Fraud Use Case Identification System | 2025-12-24 | 2025-12-27 | Dhanush | Coding | 2 – In Progress | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | System Architecture Design for Fraud Detection Engine | 2025-12-28 | 2026-01-02 | Adimulam Mourya | Design | 3 - Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Feature Extraction for Fraud Analysis | 2026-01-03 | 2026-01-07 | Adimulam Mourya | Coding | 3 - Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 11 | Machine Learning Risk Scoring Logic Integration | 2026-01-08 | 2026-01-13 | Adimulam Mourya | Coding | 3 - Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 12 | Fraud Reason Mapping and Explainability Logic | 2026-01-14 | 2026-01-17 | Dhruv | Coding | 3 - Completed | 8 | 3 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 13 | Alert Generation and Priority Assignment | 2026-01-18 | 2026-01-20 | Ashwitha | Coding | 3 - Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 14 | Backend API Development for Alerts and Transactions | 2026-01-21 | 2026-01-22 | Adimulam Mourya | Coding | 3 - Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 15 | S1 Review and Integration Validation | 2026-01-23 | 2026-01-23 | Team | Review & Testing | 3 - Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on fraud detection project requirements | Conducted detailed discussions with mentor and team members to clearly understand project objectives and scope.
Sprint 1 | Day 3 | Unclear project goals and workflow steps | Organized a team brainstorming session to finalize workflow and align tasks with project goals.
Sprint 1 | Day 4 | Confusion regarding Agile templates and documentation | Attended a mentor-led session to clarify Agile templates, defect tracker, and unit testing documents.
Sprint 1 | Day 5 | Difficulty in identifying all fraud-related use cases | Performed additional research on digital banking fraud scenarios and consulted online resources to fill information gaps.
Sprint 1 | Day 6 | Confusion in prioritizing fraud detection use cases | Created a priority matrix to rank fraud scenarios based on risk severity and importance.
Sprint 1 | Day 7 | Challenges in implementing transaction simulator logic | Collaborated with team members to debug and refine transaction simulation functionality.
Sprint 1 | Day 8 | Performance issues in rule-based fraud detection | Optimized fraud detection rules and reviewed database logic to improve execution efficiency.
Sprint 1 | Day 9 | Difficulty integrating ML risk scoring with rule-based detection | Conducted team debugging sessions to ensure smooth integration between ML scoring and rule engine.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-27 | 2025-12-02 | Adimulam Mourya | Clear requirement documentation | Assumptions without validation | Mentor discussions | Finalized project requirements
2 | Sprint 2 | 2025-12-03 | 2025-12-08 | Ashwitha | Defined workflow planning | Unstructured task execution | Team collaboration | Documented workflow and goals
3 | Sprint 3 | 2025-12-09 | 2025-12-14 | Punyavathi | Fraud use case research | Limited research sources | Use-case analysis | Identified and listed fraud scenarios
4 | Sprint 4 | 2025-12-15 | 2025-12-20 | Dhruv | Modular transaction simulator design | Hard-coded logic | Code reviews | Improved simulator structure
5 | Sprint 5 | 2025-12-21 | 2025-12-26 | Dhanush | Rule optimization techniques | Repetitive debugging | Rule validation testing | Optimized fraud detection rules
6 | Sprint 6 | 2025-12-27 | 2026-01-03 | Adimulam Mourya | ML score validation | Manual score calculation | ML integration testing | Integrated ML risk scoring
7 | Sprint 7 | 2026-01-04 | 2026-01-23 | Team | End-to-end testing & deployment